## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | RF 2/26/19
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | RF 2/26/19
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | RF 3/2/19
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | RF 3/2/19
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | RF 3/2/19
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | RF 3/2/19
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | RF 3/2/19
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | RF 3/2/19
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | RF 3/2/19
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | RK 3/2/19
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | RK 3/2/19
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | RK 3/2/19
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | RK 3/2/19
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | RK 3/2/19
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | RK 3/2/19
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | RK 3/2/19
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | RK 3/2/19
As a player, I want to be able to make moves when its my turn so That I can progress the game. | Given it is my turn when I make a move then I expect the move to be Validated and logged by the server, but not shown to other players.
Given it is my turn and I've made a move when I press submit, Then I expect the move to be finalized.
Given it is not my turn when I try to move a piece then I Expect nothing to happen.
Given it is not my turn when I press submit, then I expect nothing to Happen.
Given it is my turn and I haven’t made a move when I press submit then I expect that nothing will happen.
Given it is my turn and I haven’t made a move when I press backup Then I expect that nothing will happen.
Given it is my turn and I’ve made an unfinalized move, when I press Backup then I expect that the move will be undone.
Given it is my turn when I finalize my move then my opponent Should see the move and will then have their turn
As a player I want to move a single piece across the board to an Adjacent valid space. | Given I’’m moving a piece for my turn when a vacant dark space is diagonally across from the piece I’m moving, then I expect that moving To that space will be a valid move.
As a player , I want to move a single piece over an opponent’s piece diagonally forward and land on an adjacent vacant dark square so that I capture the opponent’s piece and It is removed from the board. | Give I’m choosing a move when one of the other player’s pieces are diagonally adjacent to my piece and the spot diagonally behind their Piece is clear, then jumping their piece with my piece is a valid move.
Given that I just made a move when I jump one of my opponent’s pieces, Then I expect that piece is captured.
Given that a jump move is available,when I want to submit my turn Then I will be required to perform that jump.
As a player, I want to move a single piece by jumping from vacant dark square to vacant dark square so that I capture an opponent’s piece each jump. | Given it’s my turn, when I jump one of the other player’s pieces and another jump move is available, then I expect that the new jump move is Required.
Given it is my turn, when I jump one of the other players pieces and another jump mov is availiable, then I expect to be able to perform that New jump.
Given it is my turn, when I jump one of the other player’s pieces and perform another jump move, then I expect that new move to be Validated.
As a player, I want to move my piece to the king-row so that my turn may end, and my piece is promoted to king by having the opponent place A second piece on top of it. | Given a piece is not a king when it moves to a space on the other side of the board from its color’s starting side then it is promoted to a king piece After the turn has ended.
As a king piece I move and jump diagonally forward or backward so that I can move to vacant dark squares and claim opponent’s pieces. | Given my piece is a king when I try to move it then I expect that Backwards moves are valid as well as forward moves.
Given my piece is a king, when I try to backwards jump a piece, then I Expect that move to be validated.
Given my piece is a king, when I try to multi jump backwards, then I Expect all moves to be validated.
As a player I want the game to end So that I can play a different game. | Given a game is in progress when I capture the last of my opponent’s Pieces then I should win the game.
Given a game is in progress when the last of my pieces are captured then I should lose the game.
Given a game is in progress,it is my turn, and I haven’t made any moves, when I cannot make a move with any of my pieces then I should Lose the game.
Given a game is in progress and it is my opponent’s turn when my opponent cannot make a move with any of their pieces then I should win The game.
Given a game is in progress when I resign from the game then I should Lose the game.
Given a game is in progress when my opponent resigns from the game Then I should win the game.
Given a game is in progress when a win/lose condition occurs and the active player has submitted their turn then no further moves can be Played and the board can be looked at in its final state.
Given a game has ended when I elect to return the home screen then I Should not be brought back to the game screen.
Given a game has ended when I’m looking at the final board state then I Should see an option to return to the home screen.
Given it is my turn when my opponent resigns the game and I subsequently submit my turn, then the move is applied, the board is Locked, and I win the game.
Given it is my turn when my opponent resigns the game and I Subsequently resign, then the board is locked, and I win the game.
As a user I want to elect and watch ongoing games so that I can learn and be entertained | Given a game has two players when I join that game then I expect to view the game as a spectator
Given I am a spectator when I am in the game then I expect to not be able to affect the board.
Given I am a spectator when I am viewing a game then I expect to see a way to leave the game.
Given I am a spectator when I am viewing a game then I expect the board to update when a player submits their turn.
Given I am a spectator when I view the game then I expect not to be dragged into a game with someone else.
Given I am a spectator when I leave a game then I expect to be redirected back to the home screen.
Given I am a player when I try to play a person spectating a different game then I expect to be given an error message.
As a user I want to replay a previously played game so that I can review the moves that were made (and otherwise enjoy it) | Given at least one game has been finished when I’m browsing selection options on the hoe page then I should see a list of all finished games.
Given I’m playing a game when that game is finished then it should appear in a list of finished games.
Given a game has been finished when I select it in a list of finished games then I should see the moves play out from beginning to end.
Given I am viewing a replay of a previous game when I hit the next button then the board should update to the next board state.
Given I view a replay of a previous game when I hit the previous button then the board should update to the previous board state.
Given I am viewing a replay of a previous game when I hit the exit button then I should be returned to the homepage.